## Sheet1
Project Timeline
Task | Start | Duration | Periods
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Hw/sw refresh | 1 | 1
Mobile business devices | 2 | 1
Staff training | 2 | 1
Website/storefront | 3 | 4
Marketing | 3 | 5
Data redundancy | 2 | 2
ERP system update | 2 | 2
Supply chain project | 4 | 4