## Slide 1: Synful Computing
Project Update
November 2023
SEPM Assignment 2 – Group 1
University of Essex
Presenter: Trevor Woodman
Nassar Al-Naimi, Charles Kuyayama, Abdulahi Alihu Ngamjeh, Trevor Woodman

## Slide 2: Introduction
Thank you for joining our team today. We have a short but informative presentation that we hope will assuage valid concerns brought up in response to the project report and specification 1 of the Synputer.
We will start by outlining our primary project milestones, and then dive into a tabled version of the concerns and issues brought up by EDC based on our last project report, and how Synful Computing will be remediating these issues prior to project completion.
Following this, we’ll take a look through our new fully costed project plan, and briefly touch on a cost estimation program that we built to assist with estimations.

## Slide 3: AGENDA
Milestones
Requirements Table
Costed Project Plan
​Cost Estimation Program
​Summary​

## Slide 4: 1. MILESTONES
Synful – Project Update – SEPM Assignment 2
Milestones
Specification 1: This system was specc’d and prototyped as per the original requirements, and unfortunately did not meet specs due to challenges.
Project Report: The project report was sent to EDC, and EDC responded: our specification came in under the requirements that were set forth for the purchase agreement between Synful and EDC.
Specification 2: This system is based on the feedback from EDC and the list of hard requirements and explicitly meets all but 2 of the requirements presented by EDC, with one of them exceeding expectation, but this will be touched on in the requirements slide.
Project Update: This presentation serves as our final update before the final specification is placed into mass production, assuming there is no feedback that would require another specification or update, but we are confident that Spec2 will meet the expectations of EDC.
EDC Order Fulfillment: Specification 2, which meets the requirements presented by EDC, is produced until completion. Assuming no major complications arise, this is approximately 129 to 134 weeks (approx. 32 to 34 months) out from today.
Consumer Market Release: The Synputer will be placed into full release, marketing will ramp up.

## Slide 5: 2. Requirements Table
REQUIREMENT | WAS IT MET? | JUSTIFICATION
Industry standard operating system | YES. Spec 2 has Synful’s popular HyperBasic operating system. | HyperBasic is a popular OS in use by previous users of Synful machines.
External keyboard/connector | YES. Spec 2 has two (2) IOP-J SC150 2ch joy/mouse/keyboard ports. | Having two IOP-J will allow dual joysticks, a mouse and keyboard, or a combination
At least 512KB of RAM | YES. Spec 2 has a whopping 2MB of RAM, using four 512KB RAM components. | Having an abundance of RAM will assist in multitasking in HB/OS GUI, accelerating productivity and usability of the system
At least 1 industry standard removable drive | YES. Spec 2 has two (2) industry standard removable storage cartridges. | Two cartridges will allow for easy emulation and storage control
SCSI expansion capability | Unfortunately, due to unit and manufacturing costs, the SCSI expansion was cut, in favour of a superior processing unit. | We determined that a SCSI expansion, which would require an additional board, was less important that a top-of-the-line CPU
At least a 68000 CPU – preferably upgradeable | YES. Spec 2 does not have a 68K, but instead comes with a far superior EP7500FE, an extremely powerful 50MHz processing unit with a 4KB cache. The board is socketed and allows for swap-out of many components, including CPU. | A top-of-the-line CPU was determined to be a better fit for a next-gen system. If that isn’t ideal for the consumer, they can take advantage of the socketed board and swap it out or later upgrade.
Minimum of 2 serial ports that support RS 422/485 standard | YES. Spec 2 has two (2) IOP-S 16550 UART 1ch serial ports | Two serial ports were requested to be part of the spec, and both conform to standards.
Board is ready to support a GUI system and mouse if required by the user | YES. Spec 2 supports a mouse, see previous requirement. The HyperBasic GUI is included in the specification. | A socketed board will allow for upgrading or swapping out RAM, CPU, etc., and supports a GUI.

## Slide 6: 3. COSTED PROJECT PLAN
Budget: £500,000 – This project plan is based off a 3-point estimation and PERT mean calculation
PESSIMISTIC | MOST LIKELY | OPTIMISTIC
Unit Cost: £697 | Unit Cost: £348.50 | Unit Cost: £174.25
Profit/unit: £-297.01 | Profit/unit: £51.49 | Profit/unit: £225.74
Labour Cost: £299,250 | Labour Cost: £217,375 | Labour Cost: £176,437.50
Labour Weeks: 189 weeks | Labour Weeks: 129 weeks | Labour Weeks: 99 weeks
Time To Completion: ~47mo to EDC fulfillment | Time To Completion: ~32mo to EDC fulfillment | Time To Completion: ~25mo to EDC fulfillment
PERT ESTIMATIONS | Mean = O + 4M + P / 6
Unit Cost | £377.54
Profit/unit | £22.45
Labour Cost | £224,197.92
Labour Weeks | 134 weeks
Time To Completion | Approximately 34 months to EDC fulfillment

## Slide 7: 4. COST ESTIMATION PROGRAM
Synful – Project Update – SEPM Assignment 2
As part of this project update, we built a cost estimation program. The previous slide’s estimates were derived from this program. Using the 3-point cost estimation technique and PERT formula, the cost estimation program compiles estimates based on three points:
Pessimistic – An estimate that is double the most-likely estimate; assumes being behind schedule, has significant delays, and low efficiency.
Most Likely – An estimate that is based on the quoted costs for components and labour; assumes that the project is on schedule, has an average number of delays, and average efficiency.
Optimistic – An estimate that is half the most-likely estimate; assumes being ahead of schedule, minimal delays, and high efficiency.
It also generates a PERT estimate for unit cost, labour cost, and labour time (in weeks).
[PROGRAM DEMO]
The program repository is available here: https://github.com/turbits/SEPM-A2-CostEstimator

## Slide 8: 5. SUMMARY
During this presentation, we have:
Outlined our milestones and expected time completion
Walked through the project requirements and our justifications for the decisions we made in specification 2
Reviewed our fully costed project plan
Had a brief overview and demo of our cost estimation program and how it has assisted us in preparing our updated project plan
We believe that this updated plan meets, or exceeds, the requirements required by EDC, and that the Synputer will outperform expectations.
Thank you for your time and have a great day.
- Synful Computing

## Slide 9: THANK YOU
Authors:
Nassar Al-Naimi
Charles Kuyayama
Abdulahi Alihu Ngamjeh
Trevor Woodman
Python Cost Estimation Repo:
https://github.com/turbits/SEPM-A2-CostEstimator